## v1803
v1803 Summary (2018/01/29)
|  | Completed Work | Remaining Work | % Completion
| Scheduled Work | Completed Work | Remaining Work | % Completion | Impact
#KEN Upgrade to v6.1 | 1253 | 312 | 840 | 27.08% | -101
WM - eGovern | 800

## #KEN
Feature 24898:Kenai Upgrade from v5.2 to v6.1 (2018/07/23)
ID | T | R | Work Order | Title | Status | Initial Estimate | Completed Work | Remaining Work | % Completion | Differential
29009 | T | R | BUG | Correction on a return with partial payment transfer | Added By Scrum Team, In Progress | 0 | 54.5 | 6 | 90.08% | 60.5
29594 | T | R | 10.03.550 | TS Staging and Technical Implementation Services | Not Started | 42 | 0 | 42 | 0% | 0
29595 | T | R | 10.04.100 | Formulas Normal | Not Started | 16 | 0 | 16 | 0% | 0
29609 | T | R | 10.04.114 | SQL Stored Procdures Normal | Not Started | 72 | 0 | 72 | 0% | 0
29611 | T | R | 10.04.116 | SQL Views Normal | Not Started | 111 | 0 | 111 | 0% | 0
29613 | T | R | 10.04.201 | Configure up to 5 “dashboards, CoolBar queries & summary screens” | Not Started | 162.5 | 0 | 162.5 | 0% | 0
29614 | T | R | 10.04.300 | (Training) OpenForms Trainning for Kenai | Not Started | 80 | 5 | 75 | 6.25% | 0
29632 | T | R | 10.05.802 | Provide Acceptance Testing Support | Not Started | 139.5 | 0 | 139.5 | 0% | 0
29633 | T | R | 10.07.123 | Provide Go-Live Support | Not Started | 24 | 0 | 24 | 0% | 0
29634 | T | R | 10.07.699 | R&D Contingency 20% | Not Started | 49 | 0 | 49 | 0% | 0
29641 | T | R | 10.04.612 | Preparations & Fix in 6.1 | In Progress | 54 | 47 | 0 | 100% | -7
29651 | T | R | 10.04.613 | Create Forms in 6.1 | In Progress | 221 | 131 | 21 | 86.18% | -69
29664 | T | R | 10.04.614 | Test Batch Process & Customization in 6.1 | In Progress | 282 | 68.5 | 60 | 53.31% | -153.5
29707 | T | R | 10.04.615 | Binary Interface needs to convert from permit to Workflow | Added By Scrum Team, In Progress |  | 4 | 4 | 50% | 8
29803 | T | R | 10.04.616 | Coordination | Added By Scrum Team |  | 2 | 58 | 3.333% | 60
[6 empty] | 1253 | 312 | 840 | 27.08% | -101
Green Description - 100% Completed
Green Differential - Under initial estimate
Red Description, must review
Red Differential - Exceed initial estimate
Yellow Description - New Items
Feature 24898:Kenai Upgrade from v5.2 to v6.1 - List Of Rejected PBI
ID | T | R | Work Order | Title | Billable Hours | Status
28997 | T | R | BUG | Wrong Payment Reapplication | 0 | Duplicate of 29009 - Not Billable
29593 | T | R | 10.03.051 | CoolBar & Summary Screen Analysis | 40 | Transfer Billable Hours to 10.04.201
29606 | T | R | 10.04.111 | Cool Bar Queries Normal | 2.5 | Transfer Billable Hours to 10.04.201
29596 | T | R | 10.04.101 | User Added Fields | 35 | Transfer Billable Hours to 29651
29597 | T | R | 10.04.102 | Property Control Forms Normal | 40 | Transfer Billable Hours to 29651
29598 | T | R | 10.04.103 | SRT Forms Complex | 48 | Transfer Billable Hours to 29651
29599 | T | R | 10.04.104 | SRT Forms Normal | 24 | Transfer Billable Hours to 29651
29600 | T | R | 10.04.105 | AR/CC Forms Complex | 32 | Transfer Billable Hours to 29651
29601 | T | R | 10.04.106 | AR/CC Forms Normal | 15 | Transfer Billable Hours to 29651
29602 | T | R | 10.04.107 | Permitting Forms Complex | 16 | Transfer Billable Hours to 29651
29603 | T | R | 10.04.108 | Permitting Forms Normal | 8 | Transfer Billable Hours to 29651
29607 | T | R | 10.04.112 | Search Screens Normal | 3 | Transfer Billable Hours to 29651
29604 | T | R | 10.04.109 | Batch Processes Normal | 72 | Transfer Billable Hours to 29664
29619 | T | R | 10.04.600 | (DEV) KEN_BR_BP_ST_InitMissingFilerEvents | 8 | Transfer Billable Hours to 29664
29620 | T | R | 10.04.601 | (DEV) KEN_BR_BP_ST_UpdateMissingFilerEvents | 8 | Transfer Billable Hours to 29664
29621 | T | R | 10.04.602 | (DEV) View Query | 5 | Transfer Billable Hours to 29664
29622 | T | R | 10.04.603 | (DEV) On Time Credit | 24 | Transfer Billable Hours to 29664
29623 | T | R | 10.04.604 | (DEV) Develop .NET AppXtender Interface | 60 | Transfer Billable Hours to 29664
29624 | T | R | 10.04.605 | (DEV) KEN_SelfReportedTax_OFActions.AccountNoFormat | 2 | Transfer Billable Hours to 29664
29625 | T | R | 10.04.606 | (DEV) KEN_BP_FileParser | 8 | Transfer Billable Hours to 29664
29626 | T | R | 10.04.607 | (DEV) KEN_BR_BP_AR_ExportCollectionAgency | 8 | Transfer Billable Hours to 29664
29627 | T | R | 10.04.608 | (DEV) KEN_BR_BP_AR_ImportCollectionAgency | 8 | Transfer Billable Hours to 29664
29628 | T | R | 10.04.609 | (DEV) BR_BP_BinaryInterface | 48 | Transfer Billable Hours to 29664
29629 | T | R | 10.04.610 | (DEV) KEN_Export_AP | 8 | Transfer Billable Hours to 29664
29615 | T | R | 10.04.301 | (Trainning) Govern Administrator (GNA) | 8 | Transfer Billable Hours to 29164
29616 | T | R | 10.04.302 | (Trainning) Govern Security Manager (GSM) | 8 | Transfer Billable Hours to 29164
29617 | T | R | 10.04.303 | (Trainning) Business Entity Designer | 16 | Transfer Billable Hours to 29164
29618 | T | R | 10.04.304 | (Trainning) OpenForms Designer | 16 | Transfer Billable Hours to 29164
29630 | T | R | 10.04.801 | (Trainning) Provide Acceptance Testing Training | 16 | Transfer Billable Hours to 29164
29631 | T | R | 10.05.800 | Test Software customizations | 23 | Transfer Billable Hours to 29664
29605 | T | R | 10.04.110 | SQL Queries | 54 | Transfer Billable Hours to 29641
29608 | T | R | 10.04.113 | SQL Stored Prcedure Complex | 48 | Transfer Billable Hours to 10.04.114
29610 | T | R | 10.04.115 | SQL Views Complex | 40 | Transfer Billable Hours to 10.04.116
29612 | T | R | 10.04.117 | SQL Views Simple | 5 | Transfer Billable Hours to 10.04.116

## #KEN Query
Project: GovernScrum Server: mtl-tfs2015\Govern Query: #KEN Upgrade to 61 List type: Flat
ID | WorkOrder# | Title | Effort | Tags | Work Item Type | Iteration Path | Priority | Release | Assigned To
24898 | - | Kenai Upgrade from v5.2 to v6.1 | 40 | #KEN | Feature | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
28997 |  | Wrong Payment Reapplication -->example : 106378 Buys Beaver Log |  | #KEN | Bug | \1809\1809.01 | 1 | 5.2.1411 | Oanh Vu
29593 | 10.03.051 | CoolBar & Summary Screen Analysis | 40 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29594 | 10.03.550 | TS Staging and Technical Implementation Services | 42 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29595 | 10.04.100 | Formulas Normal | 16 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29596 | 10.04.101 | User Added Fields | 35 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29597 | 10.04.102 | Property Control Forms Normal | 40 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29598 | 10.04.103 | SRT Forms Complex | 48 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29599 | 10.04.104 | SRT Forms Normal | 24 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29600 | 10.04.105 | AR/CC Forms Complex | 32 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29601 | 10.04.106 | AR/CC Forms Normal | 15 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29602 | 10.04.107 | Permitting Forms Complex | 16 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29603 | 10.04.108 | Permitting Forms Normal | 8 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29604 | 10.04.109 | Batch Processes Normal | 72 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29605 | 10.04.110 | SQL Queries | 54 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29606 | 10.04.111 | Cool Bar Queries Normal | 2.5 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29607 | 10.04.112 | Search Screens Normal | 3 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29608 | 10.04.113 | SQL Stored Prcedure Complex | 48 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29609 | 10.04.114 | SQL Stored Procdures Normal | 24 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29610 | 10.04.115 | SQL Views Complex | 40 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29611 | 10.04.116 | SQL Views Normal | 66 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29612 | 10.04.117 | SQL Views Simple | 5 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29613 | 10.04.201 | Configure up to 5 “dashboards, CoolBar queries & summary screens” | 120 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29614 | 10.04.300 | (Trainning) OpenForms Overview & New Features | 16 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29615 | 10.04.301 | (Trainning) Govern Administrator (GNA) | 8 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29616 | 10.04.302 | (Trainning) Govern Security Manager (GSM) | 8 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29617 | 10.04.303 | (Trainning) Business Entity Designer | 16 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29618 | 10.04.304 | (Trainning) OpenForms Designer | 16 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29619 | 10.04.600 | (DEV) KEN_BR_BP_ST_InitMissingFilerEvents | 8 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29620 | 10.04.601 | (DEV) KEN_BR_BP_ST_UpdateMissingFilerEvents | 8 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29621 | 10.04.602 | (DEV) View Query | 5 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29622 | 10.04.603 | (DEV) On Time Credit | 24 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29623 | 10.04.604 | (DEV) Develop .NET AppXtender Interface | 60 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29624 | 10.04.605 | (DEV) KEN_SelfReportedTax_OFActions.AccountNoFormat | 2 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29625 | 10.04.606 | (DEV) KEN_BP_FileParser | 8 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29626 | 10.04.607 | (DEV) KEN_BR_BP_AR_ExportCollectionAgency | 8 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29627 | 10.04.608 | (DEV) KEN_BR_BP_AR_ImportCollectionAgency | 8 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29628 | 10.04.609 | (DEV) BR_BP_BinaryInterface | 48 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29629 | 10.04.610 | (DEV) KEN_Export_AP | 8 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29630 | 10.04.801 | (Trainning) Provide Acceptance Testing Training | 16 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29631 | 10.05.800 | Test Software customizations | 23 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29632 | 10.05.802 | Provide Acceptance Testing Support | 139.5 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29633 | 10.07.123 | Provide Go-Live Support | 24 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>
29634 | 10.07.699 | R&D Contingency 20% | 49 | #KEN | Product Backlog Item | \1809\1809.01 | 2 | 6.1.1803 | Benoit Lauzon <HARRIS\blauzon>

## WM - eGovern
#KEN Upgrade to v6.1 (2018/07/03)
ID | T | R | Work Order | Title | Status | Initial Estimate | Completed Work | Remaining Work | % Completion | Differential
29593 | T | R | 10.03.051 | CoolBar & Summary Screen Analysis |  | 40 | 0 | 0 | 0 | 0
29594 | T | R | 10.03.550 | TS Staging and Technical Implementation Services |  | 42 | 0 | 0 | 0 | 0
29595 | T | R | 10.04.100 | Formulas Normal |  | 16 | 0 | 0 | 0 | 0
29596 | T | R | 10.04.101 | User Added Fields |  | 35 | 0 | 0 | 0 | 0
29597 | T | R | 10.04.102 | Property Control Forms Normal |  | 40 | 0 | 0 | 0 | 0
29598 | T | R | 10.04.103 | SRT Forms Complex |  | 48 | 0 | 0 | 0 | 0
29599 | T | R | 10.04.104 | SRT Forms Normal |  | 24 | 0 | 0 | 0 | 0
29600 | T | R | 10.04.105 | AR/CC Forms Complex |  | 32 | 0 | 0 | 0 | 0
29601 | T | R | 10.04.106 | AR/CC Forms Normal |  | 15 | 0 | 0 | 0 | 0
29602 | T | R | 10.04.107 | Permitting Forms Complex |  | 16 | 0 | 0 | 0 | 0
29603 | T | R | 10.04.108 | Permitting Forms Normal |  | 8 | 0 | 0 | 0 | 0
29604 | T | R | 10.04.109 | Batch Processes Normal |  | 72 | 0 | 0 | 0 | 0
29605 | T | R | 10.04.110 | SQL Queries |  | 54 | 0 | 0 | 0 | 0
29606 | T | R | 10.04.111 | Cool Bar Queries Normal |  | 2.5 | 0 | 0 | 0 | 0
29607 | T | R | 10.04.112 | Search Screens Normal |  | 3 | 0 | 0 | 0 | 0
29608 | T | R | 10.04.113 | SQL Stored Prcedure Complex |  | 48 | 0 | 0 | 0 | 0
29609 | T | R | 10.04.114 | SQL Stored Procdures Normal |  | 24 | 0 | 0 | 0 | 0
29610 | T | R | 10.04.115 | SQL Views Complex |  | 40 | 0 | 0 | 0 | 0
29611 | T | R | 10.04.116 | SQL Views Normal |  | 66 | 0 | 0 | 0 | 0
29612 | T | R | 10.04.117 | SQL Views Simple |  | 5 | 0 | 0 | 0 | 0
29613 | T | R | 10.04.201 | Configure up to 5 “dashboards, CoolBar queries & summary screens” |  | 120 | 0 | 0 | 0 | 0
29614 | T | R | 10.04.300 | (Trainning) OpenForms Overview & New Features |  | 16 | 0 | 0 | 0 | 0
29615 | T | R | 10.04.301 | (Trainning) Govern Administrator (GNA) |  | 8 | 0 | 0 | 0 | 0
29616 | T | R | 10.04.302 | (Trainning) Govern Security Manager (GSM) |  | 8 | 0 | 0 | 0 | 0
29617 | T | R | 10.04.303 | (Trainning) Business Entity Designer |  | 16 | 0 | 0 | 0 | 0
29618 | T | R | 10.04.304 | (Trainning) OpenForms Designer |  | 16 | 0 | 0 | 0 | 0
29619 | T | R | 10.04.600 | (DEV) KEN_BR_BP_ST_InitMissingFilerEvents |  | 8 | 0 | 0 | 0 | 0
29620 | T | R | 10.04.601 | (DEV) KEN_BR_BP_ST_UpdateMissingFilerEvents |  | 8 | 0 | 0 | 0 | 0
29621 | T | R | 10.04.602 | (DEV) View Query |  | 5 | 0 | 0 | 0 | 0
29622 | T | R | 10.04.603 | (DEV) On Time Credit |  | 24 | 0 | 0 | 0 | 0
29623 | T | R | 10.04.604 | (DEV) Develop .NET AppXtender Interface |  | 60 | 0 | 0 | 0 | 0
29624 | T | R | 10.04.605 | (DEV) KEN_SelfReportedTax_OFActions.AccountNoFormat |  | 2 | 0 | 0 | 0 | 0
29625 | T | R | 10.04.606 | (DEV) KEN_BP_FileParser |  | 8 | 0 | 0 | 0 | 0
29626 | T | R | 10.04.607 | (DEV) KEN_BR_BP_AR_ExportCollectionAgency |  | 8 | 0 | 0 | 0 | 0
29627 | T | R | 10.04.608 | (DEV) KEN_BR_BP_AR_ImportCollectionAgency |  | 8 | 0 | 0 | 0 | 0
29628 | T | R | 10.04.609 | (DEV) BR_BP_BinaryInterface |  | 48 | 0 | 0 | 0 | 0
29629 | T | R | 10.04.610 | (DEV) KEN_Export_AP |  | 8 | 0 | 0 | 0 | 0
29630 | T | R | 10.04.801 | (Trainning) Provide Acceptance Testing Training |  | 16 | 0 | 0 | 0 | 0
29631 | T | R | 10.05.800 | Test Software customizations |  | 23 | 0 | 0 | 0 | 0
29632 | T | R | 10.05.802 | Provide Acceptance Testing Support |  | 139.5 | 0 | 0 | 0 | 0
29633 | T | R | 10.07.123 | Provide Go-Live Support |  | 24 | 0 | 0 | 0 | 0
29634 | T | R | 10.07.699 | R&D Contingency 20% |  | 49 | 0 | 0 | 0 | 0
0
[6 empty] | 1253 | 0 | 0 | 0% | 0
Reserved Hours | [6 empty] | 0
Work Hours | [6 empty] | 0
Impact on Roadmap (Hours) | [6 empty] | 0
Green Cells - Completed
Red Description, must review
Red Differential - Exceed initial estimate

## Variables
Refresh All / Publish All
Report URL | http://mrn-tfs-p02/ReportServer/Pages/ReportViewer.aspx?%2fPBI&rc:Parameters=false&rs:Command=Render&ID=
TFS | http://mtl-tfs2015:8080/tfs/Govern/GovernScrum/_workitems?_a=edit&id=

## VSTS_ValidationWS_1 (hidden)
value doesn't matter | value doesn't matter | value doesn't matter | value doesn't matter | \ | \ | Select User... | 1 | 4.7.1603 | Select User... | 1 | 4.7.1603 | Select User... | Done | 1 | Select User... | 1 | 4.7.1603 | Select User... | 1 | Select User... | 1 | 4.7.1603 | Select User... | 1 | 4.7.1603 | Select User... | 1 | Select User... | Billable Work | Select User... | 1 | 4.7.1603
readOnlyTestRange_@ | readOnlyTestRange_0 | readOnlyTestRange_M/d/yyyy h:mm AM/PM | readOnlyTestRange_General | \KB | \1806 | Angela Bowen <HARRIS\ab14688> | 2 | 5.1.1407 | Angela Bowen <HARRIS\ab14688> | 2 | 5.1.1407 | Angela Bowen <HARRIS\ab14688> | In Progress | 2 | Angela Bowen <HARRIS\ab14688> | 2 | 5.1.1407 | Angela Bowen <HARRIS\ab14688> | 2 | Angela Bowen <HARRIS\ab14688> | 2 | 5.1.1407 | Angela Bowen <HARRIS\ab14688> | 2 | 5.1.1407 | Angela Bowen <HARRIS\ab14688> | 2 | Angela Bowen <HARRIS\ab14688> | Bug | Angela Bowen <HARRIS\ab14688> | 2 | 5.1.1407
|  |  |  | \PS | \1806\1806.01 | Aurelia Pitic Secelean | 3 | 5.2.1411 | Aurelia Pitic Secelean | 3 | 5.2.1411 | Aurelia Pitic Secelean | New | 3 | Aurelia Pitic Secelean | 3 | 5.2.1411 | Aurelia Pitic Secelean | 3 | Aurelia Pitic Secelean | 3 | 5.2.1411 | Aurelia Pitic Secelean | 3 | 5.2.1411 | Aurelia Pitic Secelean | 3 | Aurelia Pitic Secelean | Epic | Aurelia Pitic Secelean | 3 | 5.2.1411
|  |  |  | \QA | \1806\1806.02 | Benoit Lauzon <HARRIS\blauzon> | 4 | 6.0.1606 | Benoit Lauzon <HARRIS\blauzon> | 4 | 6.0.1606 | Benoit Lauzon <HARRIS\blauzon> | Removed | 4 | Benoit Lauzon <HARRIS\blauzon> | 4 | 6.0.1606 | Benoit Lauzon <HARRIS\blauzon> | 4 | Benoit Lauzon <HARRIS\blauzon> | 4 | 6.0.1606 | Benoit Lauzon <HARRIS\blauzon> | 4 | 6.0.1606 | Benoit Lauzon <HARRIS\blauzon> | 4 | Benoit Lauzon <HARRIS\blauzon> | Feature | Benoit Lauzon <HARRIS\blauzon> | 4 | 6.0.1606
|  |  |  | \Scrumban | \1806\1806.03 | Bill Albert | VSTS_ada7b77f_d823_4e85_81ad_c1a3f2045c3d_A9-74-3C-60-20-83-BF-D2-70-44-DA-6E-AF-8C-55-96-9A-24-CE-B3 | 6.0.1609 | Bill Albert | all_VSTS_ada7b77f_d823_4e85_81ad_c1a3f2045c3d_Bug_Microsoft.VSTS.Common.Priority | 6.0.1609 | Bill Albert |  | all_VSTS_ada7b77f_d823_4e85_81ad_c1a3f2045c3d_Epic_Microsoft.VSTS.Common.Priority | Bill Albert | all_VSTS_ada7b77f_d823_4e85_81ad_c1a3f2045c3d_Feature_Microsoft.VSTS.Common.Priority | 6.0.1609 | Bill Albert | all_VSTS_ada7b77f_d823_4e85_81ad_c1a3f2045c3d_Impediment_Microsoft.VSTS.Common.Priority | Bill Albert | all_VSTS_ada7b77f_d823_4e85_81ad_c1a3f2045c3d_Product Backlog Item_Microsoft.VSTS.Common.Priority | 6.0.1609 | Bill Albert | all_VSTS_ada7b77f_d823_4e85_81ad_c1a3f2045c3d_Task_Microsoft.VSTS.Common.Priority | 6.0.1609 | Bill Albert | all_VSTS_ada7b77f_d823_4e85_81ad_c1a3f2045c3d_Test Case_Microsoft.VSTS.Common.Priority | Bill Albert | Impediment | Bill Albert | all_VSTS_ada7b77f_d823_4e85_81ad_c1a3f2045c3d_Microsoft.VSTS.Common.Priority | 6.0.1609
|  |  |  | \Support | \1806\1806.04 | Bill Koperski <HARRIS\bkoperski> |  | 6.0.1611 | Bill Koperski <HARRIS\bkoperski> |  | 6.0.1611 | Bill Koperski <HARRIS\bkoperski> |  |  | Bill Koperski <HARRIS\bkoperski> |  | 6.0.1611 | Bill Koperski <HARRIS\bkoperski> |  | Bill Koperski <HARRIS\bkoperski> |  | 6.0.1611 | Bill Koperski <HARRIS\bkoperski> |  | 6.0.1611 | Bill Koperski <HARRIS\bkoperski> |  | Bill Koperski <HARRIS\bkoperski> | Product Backlog Item | Bill Koperski <HARRIS\bkoperski> |  | 6.0.1611
|  |  |  | all_VSTS_ada7b77f_d823_4e85_81ad_c1a3f2045c3d_System.AreaPath | \1806\1806.05 | Bonnie Brown-holmes |  | 6.0.1706 | Bonnie Brown-holmes |  | 6.0.1706 | Bonnie Brown-holmes |  |  | Bonnie Brown-holmes |  | 6.0.1706 | Bonnie Brown-holmes |  | Bonnie Brown-holmes |  | 6.0.1706 | Bonnie Brown-holmes |  | 6.0.1706 | Bonnie Brown-holmes |  | Bonnie Brown-holmes | Task | Bonnie Brown-holmes |  | 6.0.1706
[5 empty] | \1806\1806.06 | CCB MSGovern |  | 6.0.1803 | CCB MSGovern |  | 6.0.1803 | CCB MSGovern |  |  | CCB MSGovern |  | 6.0.1803 | CCB MSGovern |  | CCB MSGovern |  | 6.0.1803 | CCB MSGovern |  | 6.0.1803 | CCB MSGovern |  | CCB MSGovern | Test Case | CCB MSGovern |  | 6.0.1803
[5 empty] | \1809 | Cynthia Hayes |  | 6.1.1611 | Cynthia Hayes |  | 6.1.1611 | Cynthia Hayes |  |  | Cynthia Hayes |  | 6.1.1611 | Cynthia Hayes |  | Cynthia Hayes |  | 6.1.1611 | Cynthia Hayes |  | 6.1.1611 | Cynthia Hayes |  | Cynthia Hayes | all_VSTS_ada7b77f_d823_4e85_81ad_c1a3f2045c3d_System.WorkItemType | Cynthia Hayes |  | 6.1.1611
[5 empty] | \1809\1809.01 | Cyril Viron <HARRIS\cviron> |  | 6.1.1706 | Cyril Viron <HARRIS\cviron> |  | 6.1.1706 | Cyril Viron <HARRIS\cviron> |  |  | Cyril Viron <HARRIS\cviron> |  | 6.1.1706 | Cyril Viron <HARRIS\cviron> |  | Cyril Viron <HARRIS\cviron> |  | 6.1.1706 | Cyril Viron <HARRIS\cviron> |  | 6.1.1706 | Cyril Viron <HARRIS\cviron> |  | Cyril Viron <HARRIS\cviron> |  | Cyril Viron <HARRIS\cviron> |  | 6.1.1706
[5 empty] | \1809\1809.02 | Daniel Vendette |  | 6.1.1803 | Daniel Vendette |  | 6.1.1803 | Daniel Vendette |  |  | Daniel Vendette |  | 6.1.1803 | Daniel Vendette |  | Daniel Vendette |  | 6.1.1803 | Daniel Vendette |  | 6.1.1803 | Daniel Vendette |  | Daniel Vendette |  | Daniel Vendette |  | 6.1.1803
[5 empty] | \1809\1809.03 | Darlene Franck <HARRIS\dfranck> |  | TBD | Darlene Franck <HARRIS\dfranck> |  | TBD | Darlene Franck <HARRIS\dfranck> |  |  | Darlene Franck <HARRIS\dfranck> |  | TBD | Darlene Franck <HARRIS\dfranck> |  | Darlene Franck <HARRIS\dfranck> |  | TBD | Darlene Franck <HARRIS\dfranck> |  | TBD | Darlene Franck <HARRIS\dfranck> |  | Darlene Franck <HARRIS\dfranck> |  | Darlene Franck <HARRIS\dfranck> |  | TBD
[5 empty] | \1809\1809.04 | Eric Martineau <HARRIS\emartineau> |  | VB6 | Eric Martineau <HARRIS\emartineau> |  | VB6 | Eric Martineau <HARRIS\emartineau> |  |  | Eric Martineau <HARRIS\emartineau> |  | VB6 | Eric Martineau <HARRIS\emartineau> |  | Eric Martineau <HARRIS\emartineau> |  | VB6 | Eric Martineau <HARRIS\emartineau> |  | VB6 | Eric Martineau <HARRIS\emartineau> |  | Eric Martineau <HARRIS\emartineau> |  | Eric Martineau <HARRIS\emartineau> |  | VB6
[5 empty] | \1809\1809.05 | Eric Plante |  | VSTS_ada7b77f_d823_4e85_81ad_c1a3f2045c3d_DE-A2-94-4C-04-9B-27-90-6B-01-52-18-16-64-84-19-1C-D9-37-8A | Eric Plante |  | all_VSTS_ada7b77f_d823_4e85_81ad_c1a3f2045c3d_Bug_govern.Release | Eric Plante |  |  | Eric Plante |  | all_VSTS_ada7b77f_d823_4e85_81ad_c1a3f2045c3d_Feature_govern.Release | Eric Plante |  | Eric Plante |  | all_VSTS_ada7b77f_d823_4e85_81ad_c1a3f2045c3d_Product Backlog Item_govern.Release | Eric Plante |  | all_VSTS_ada7b77f_d823_4e85_81ad_c1a3f2045c3d_Task_govern.Release | Eric Plante |  | Eric Plante |  | Eric Plante |  | all_VSTS_ada7b77f_d823_4e85_81ad_c1a3f2045c3d_govern.Release
[5 empty] | \1809\1809.06 | George Mirea <HARRIS\gmirea> |  |  | George Mirea <HARRIS\gmirea> |  |  | George Mirea <HARRIS\gmirea> |  |  | George Mirea <HARRIS\gmirea> |  |  | George Mirea <HARRIS\gmirea> |  | George Mirea <HARRIS\gmirea> |  |  | George Mirea <HARRIS\gmirea> |  |  | George Mirea <HARRIS\gmirea> |  | George Mirea <HARRIS\gmirea> |  | George Mirea <HARRIS\gmirea>
[5 empty] | \1811 | Hernan Alonso |  |  | Hernan Alonso |  |  | Hernan Alonso |  |  | Hernan Alonso |  |  | Hernan Alonso |  | Hernan Alonso |  |  | Hernan Alonso |  |  | Hernan Alonso |  | Hernan Alonso |  | Hernan Alonso
[5 empty] | \1811\1811.01 | Jane Cormack <HARRIS\jcormack> |  |  | Jane Cormack <HARRIS\jcormack> |  |  | Jane Cormack <HARRIS\jcormack> |  |  | Jane Cormack <HARRIS\jcormack> |  |  | Jane Cormack <HARRIS\jcormack> |  | Jane Cormack <HARRIS\jcormack> |  |  | Jane Cormack <HARRIS\jcormack> |  |  | Jane Cormack <HARRIS\jcormack> |  | Jane Cormack <HARRIS\jcormack> |  | Jane Cormack <HARRIS\jcormack>
[5 empty] | \1811\1811.02 | Jeffrey Hohenstein |  |  | Jeffrey Hohenstein |  |  | Jeffrey Hohenstein |  |  | Jeffrey Hohenstein |  |  | Jeffrey Hohenstein |  | Jeffrey Hohenstein |  |  | Jeffrey Hohenstein |  |  | Jeffrey Hohenstein |  | Jeffrey Hohenstein |  | Jeffrey Hohenstein
[5 empty] | \1811\1811.03 | Jimmy Giang |  |  | Jimmy Giang |  |  | Jimmy Giang |  |  | Jimmy Giang |  |  | Jimmy Giang |  | Jimmy Giang |  |  | Jimmy Giang |  |  | Jimmy Giang |  | Jimmy Giang |  | Jimmy Giang
[5 empty] | \1811\1811.RT | Kar Wing Tam |  |  | Kar Wing Tam |  |  | Kar Wing Tam |  |  | Kar Wing Tam |  |  | Kar Wing Tam |  | Kar Wing Tam |  |  | Kar Wing Tam |  |  | Kar Wing Tam |  | Kar Wing Tam |  | Kar Wing Tam
[5 empty] | \1903 | Laurie Graham |  |  | Laurie Graham |  |  | Laurie Graham |  |  | Laurie Graham |  |  | Laurie Graham |  | Laurie Graham |  |  | Laurie Graham |  |  | Laurie Graham |  | Laurie Graham |  | Laurie Graham
[5 empty] | \1906 | Liz Remington |  |  | Liz Remington |  |  | Liz Remington |  |  | Liz Remington |  |  | Liz Remington |  | Liz Remington |  |  | Liz Remington |  |  | Liz Remington |  | Liz Remington |  | Liz Remington
[5 empty] | \1909 | M'Hammed Kettani <HARRIS\mkettani> |  |  | M'Hammed Kettani <HARRIS\mkettani> |  |  | M'Hammed Kettani <HARRIS\mkettani> |  |  | M'Hammed Kettani <HARRIS\mkettani> |  |  | M'Hammed Kettani <HARRIS\mkettani> |  | M'Hammed Kettani <HARRIS\mkettani> |  |  | M'Hammed Kettani <HARRIS\mkettani> |  |  | M'Hammed Kettani <HARRIS\mkettani> |  | M'Hammed Kettani <HARRIS\mkettani> |  | M'Hammed Kettani <HARRIS\mkettani>
[5 empty] | \1911 | Mark Piller |  |  | Mark Piller |  |  | Mark Piller |  |  | Mark Piller |  |  | Mark Piller |  | Mark Piller |  |  | Mark Piller |  |  | Mark Piller |  | Mark Piller |  | Mark Piller
[5 empty] | \Past Release | Michelle Gagne <HARRIS\micgagne> |  |  | Michelle Gagne <HARRIS\micgagne> |  |  | Michelle Gagne <HARRIS\micgagne> |  |  | Michelle Gagne <HARRIS\micgagne> |  |  | Michelle Gagne <HARRIS\micgagne> |  | Michelle Gagne <HARRIS\micgagne> |  |  | Michelle Gagne <HARRIS\micgagne> |  |  | Michelle Gagne <HARRIS\micgagne> |  | Michelle Gagne <HARRIS\micgagne> |  | Michelle Gagne <HARRIS\micgagne>
[5 empty] | \Past Release\1603 | Miguel Miranda |  |  | Miguel Miranda |  |  | Miguel Miranda |  |  | Miguel Miranda |  |  | Miguel Miranda |  | Miguel Miranda |  |  | Miguel Miranda |  |  | Miguel Miranda |  | Miguel Miranda |  | Miguel Miranda
[5 empty] | \Past Release\1606 | Naiara Fraga <HARRIS\NFraga> |  |  | Naiara Fraga <HARRIS\NFraga> |  |  | Naiara Fraga <HARRIS\NFraga> |  |  | Naiara Fraga <HARRIS\NFraga> |  |  | Naiara Fraga <HARRIS\NFraga> |  | Naiara Fraga <HARRIS\NFraga> |  |  | Naiara Fraga <HARRIS\NFraga> |  |  | Naiara Fraga <HARRIS\NFraga> |  | Naiara Fraga <HARRIS\NFraga> |  | Naiara Fraga <HARRIS\NFraga>
[5 empty] | \Past Release\1606\1606.01 | Oanh Vu |  |  | Oanh Vu |  |  | Oanh Vu |  |  | Oanh Vu |  |  | Oanh Vu |  | Oanh Vu |  |  | Oanh Vu |  |  | Oanh Vu |  | Oanh Vu |  | Oanh Vu
[5 empty] | \Past Release\1606\1606.02 | Olusegun Olaniyan |  |  | Olusegun Olaniyan |  |  | Olusegun Olaniyan |  |  | Olusegun Olaniyan |  |  | Olusegun Olaniyan |  | Olusegun Olaniyan |  |  | Olusegun Olaniyan |  |  | Olusegun Olaniyan |  | Olusegun Olaniyan |  | Olusegun Olaniyan
[5 empty] | \Past Release\1606\1606.03 | Shaun Larouche |  |  | Shaun Larouche |  |  | Shaun Larouche |  |  | Shaun Larouche |  |  | Shaun Larouche |  | Shaun Larouche |  |  | Shaun Larouche |  |  | Shaun Larouche |  | Shaun Larouche |  | Shaun Larouche
[5 empty] | \Past Release\1606\1606.04 | Stephen Li |  |  | Stephen Li |  |  | Stephen Li |  |  | Stephen Li |  |  | Stephen Li |  | Stephen Li |  |  | Stephen Li |  |  | Stephen Li |  | Stephen Li |  | Stephen Li
[5 empty] | \Past Release\1606\1606.05 | Sylvain Hudon |  |  | Sylvain Hudon |  |  | Sylvain Hudon |  |  | Sylvain Hudon |  |  | Sylvain Hudon |  | Sylvain Hudon |  |  | Sylvain Hudon |  |  | Sylvain Hudon |  | Sylvain Hudon |  | Sylvain Hudon
[5 empty] | \Past Release\1606\1606.06 | Zahir Kaci |  |  | Zahir Kaci |  |  | Zahir Kaci |  |  | Zahir Kaci |  |  | Zahir Kaci |  | Zahir Kaci |  |  | Zahir Kaci |  |  | Zahir Kaci |  | Zahir Kaci |  | Zahir Kaci
[5 empty] | \Past Release\1606\1606.RT | all_VSTS_ada7b77f_d823_4e85_81ad_c1a3f2045c3d_Billable Work_System.AssignedTo |  |  | VSTS_ada7b77f_d823_4e85_81ad_c1a3f2045c3d_71-AF-E3-7B-31-DB-0D-DE-6E-67-42-C7-35-38-12-06-D9-F7-43-8B |  |  | all_VSTS_ada7b77f_d823_4e85_81ad_c1a3f2045c3d_Bug_System.AssignedTo |  |  | all_VSTS_ada7b77f_d823_4e85_81ad_c1a3f2045c3d_Epic_System.AssignedTo |  |  | all_VSTS_ada7b77f_d823_4e85_81ad_c1a3f2045c3d_Feature_System.AssignedTo |  | all_VSTS_ada7b77f_d823_4e85_81ad_c1a3f2045c3d_Impediment_System.AssignedTo |  |  | all_VSTS_ada7b77f_d823_4e85_81ad_c1a3f2045c3d_Product Backlog Item_System.AssignedTo |  |  | all_VSTS_ada7b77f_d823_4e85_81ad_c1a3f2045c3d_Task_System.AssignedTo |  | all_VSTS_ada7b77f_d823_4e85_81ad_c1a3f2045c3d_Test Case_System.AssignedTo |  | all_VSTS_ada7b77f_d823_4e85_81ad_c1a3f2045c3d_System.AssignedTo
\Past Release\1609
\Past Release\1609\1609.01
\Past Release\1609\1609.02
\Past Release\1609\1609.03
\Past Release\1609\1609.04
\Past Release\1609\1609.05
\Past Release\1609\1609.06
\Past Release\1609\1609.RT
\Past Release\1611
\Past Release\1611\1611.01
\Past Release\1611\1611.02
\Past Release\1611\1611.03
\Past Release\1611\1611.RT
\Past Release\1703
\Past Release\1703\1703.01
\Past Release\1703\1703.03
\Past Release\1703\1703.04
\Past Release\1703\1703.05
\Past Release\1703\1703.06
\Past Release\1703\1703.07
\Past Release\1703\1703.RT
\Past Release\1706
\Past Release\1706\1706.01
\Past Release\1706\1706.02
\Past Release\1706\1706.03
\Past Release\1706\1706.04
\Past Release\1706\1706.05
\Past Release\1706\1706.06
\Past Release\1706\1706.07
\Past Release\1706\1706.08
\Past Release\1709
\Past Release\1709\1709.01
\Past Release\1709\1709.02
\Past Release\1709\1709.03
\Past Release\1709\1709.04
\Past Release\1711
\Past Release\1711\1711.01
\Past Release\1711\1711.02
\Past Release\1711\1711.03
\Past Release\1711\1711.04
\Past Release\1803
\Past Release\1803\1803.01
\Past Release\1803\1803.02
\Past Release\1803\1803.03
\Past Release\1803\1803.04
\Past Release\1803\1803.05
\Past Release\1803\1803.06
\Past Release\1803\1803.07
\PS
\PS\Items for Review
\PS\Part 05- Due 6.15
\PS\Post Go Live Reports
\PS\Post Go-Live Enhancements
\PS\Sprint 1- 6.18-8.10
\PS\Sprint 2 08.13-09.14
\PS\Sprint 3 09.17-10.19
\PS\Sprint 4 10.22-11.16
\PS\Sprint 5 11.19-12.31
\PS\Sprint 6 1.1-1.31
\PS\Sprint 7- 2.1-2.28
\PS\Sprint 8- 3.1-3.29
\PS\Sprint 9- 4.1-4.30
all_VSTS_ada7b77f_d823_4e85_81ad_c1a3f2045c3d_System.IterationPath